## Simplified Register
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
2017-02-21 | 1 | task 2.2 Smolt probability of encounter model - data sharing | NA | External | N. Johnson (environmental) | 8 | 4 | Med | facilitate conversations with Umaine on data sharing | 6 | 2 | Low
2017-02-21 | 2 | Task 5 Ice data collected | NA | External | J. Kasper (UAA lead) | 6 | 6 | Med | real time data collection implemented | 2 | 4 | Low
2017-02-21 | 3 | Permitting/Licensing complete for in water testing | Multiple (or all) life phases | External | N. Johnson (environmental) | 8 | 8 | High | FERC Final license application submittal scheudled for 12/17 | 6 | 8 | Med
2017-02-21 | 4 | Generator Final Design | Pre-construction | Technical | R. Tyler (lead engineer) | 8 | 6 | Med | Design reviews and component validation testing | 4 | 6 | Med
2017-02-21 | 5 | Generator Procurement | Commissioning | Commercial | R. Tyler (lead engineer) | 8 | 6 | Med | Ensure Generator delivery by 2/2018 to allow adequate time for testing using project development plan with regular status reports | 6 | 6 | Med
2017-02-21 | 6 | Buoyancy System Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 4 | 4 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 2 | 6 | Low
2017-02-21 | 7 | Structural Assembly Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 6 | 6 | Med | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | 4 | 6 | Med
2017-02-21 | 8 | Turbine Procuement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 8 | 6 | Med | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | 4 | 6 | Med
2017-02-21 | 9 | Power Electronics Procurement | Multiple (or all) life phases | Commercial | M. Worthington (Project Management) | 8 | 6 | Med | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | 6 | 6 | Med
2017-02-21 | 10 | SCADA Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 8 | 6 | Med | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 6 | 6 | Med
2017-02-21 | 11 | power and Data cable procurement | Multiple (or all) life phases | Commercial | M. Worthington (Project Management) | 8 | 6 | Med | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 6 | 6 | Med
2017-02-21 | 12 | Mooring Sytem Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 6 | 6 | Med | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 2 | 6 | Low
2017-02-21 | 13 | Dirveline Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 8 | 6 | Med | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | 4 | 6 | Med
2017-02-21 | 14 | Mechanical Brake Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 8 | 6 | Med | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | 4 | 6 | Med
2017-02-21 | 15 | Mechanical Brake Procurement | Multiple (or all) life phases | Commercial | R. Tyler (lead engineer) | 8 | 6 | Med | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | 4 | 6 | Med
2017-02-21 | 16 | Buoyancy System Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 6 | 8 | Med | Utilizing Incremetnal improvements to a proven concept, add redundancy to design Perform land based tests in May 2017 and move on to on water validation tests prior to shipment to Igiugig | 4 | 6 | Med
2017-02-21 | 17 | Structural Assembly Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 6 | 8 | Med | FEA analysis of structure include load factors following DNV standards and considers extreme loading conditions such as uneven bottom and detalied CAD models for subsystem interfaces vlaidation tests to ensure strucutral integrityu meets specs incorporate structural redundancy | 4 | 6 | Med
2017-02-21 | 18 | Turbine Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 6 | 6 | Med | Utilize CFD as design tool for performance validation, FEA analysis of turbines include load factors following DNV standards and considers extreme loading conditions, secondary design input from composite manufacturer | 4 | 6 | Med
2017-02-21 | 19 | Generator Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 8 | 6 | Med | Factory Accpetance testing and laboratory testing of Genertor integrated with Power elecrtornics to ensure compatibility | 4 | 6 | Med
2017-02-21 | 20 | Power Electronics Validation | Multiple (or all) life phases | Technical | M. Worthington (Project Management) | 8 | 6 | Med | Factory accpetance tests and sequenced laboratory testing to ensure Power Electronics meets requirements before shipment | 6 | 6 | Med
2017-02-21 | 21 | SCADA Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 8 | 6 | Med | Factory accpetance tests and sequenced laboratory testing to ensure SCADA meets requirements before shipment | 6 | 6 | Med
2017-02-21 | 22 | power and Data cable validation | Multiple (or all) life phases | Technical | M. Worthington (Project Management) | 6 | 8 | Med | Utilize proven cable technology utilize secondary cable armor in high risk areas utilize redundant conductors for data and fiber optic, reduce inspections and associated wear and tear | 4 | 8 | Med
2017-02-21 | 23 | Mooring Sytem Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 6 | 10 | High | Design to DNV standards, utilize geophyisical knowledge and seek industry expertise to specify mooring system components, consider most favorable failure modes | 4 | 10 | Med
2017-02-21 | 24 | Dirveline Validation | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 8 | 8 | High | Throught validation testing, desing system for increased operational tolerances and loads, choosed components with long service life and minimal maintenance and alignement requirements increase modularity for replacement | 6 | 8 | Med
2017-02-21 | 25 | Mechanical Brake | Multiple (or all) life phases | Technical | R. Tyler (lead engineer) | 8 | 8 | High | Throught validation testing, redundant electrical brake, Rely on third party expertise for design | 6 | 6 | Med
2017-02-24 | 26 | Receipt of all permits and licesenses | Multiple (or all) life phases | External | N. Johnson (environmental) | 8 | 10 | High | Continue regular dialogue with regulatory agencies after final pilot license and other permit applications, respond to AIRs in timely manner | 6 | 10 | High
2017-02-24 | 27 | Component delivery to Igiugig | Transportation | Management | M. Worthington (Project Management) | 6 | 8 | Med | Track project schedule, align component validation and delivery to port of shipment with shipper schedules, ship components early if possible arrival on first barge of season (June 2018) or second (Jluy 2018) at latest | 4 | 8 | Med
2017-02-24 | 28 | Device assmebly | Commissioning | Technical | R. Tyler (lead engineer) | 6 | 8 | Med | Device assembly is fdifficult or requires workaround in Igiugig due to component interfaces, component damage during shipment, or other. Timing June-August 2018 | 4 | 8 | Med
2017-02-24 | 29 | Power System /comissioning issues | Commissioning | Technical | M. Worthington (Project Management) | 6 | 10 | High | prior device testing and component testing in Nikiksi and elsewhere will reduce unexpected issues with deployment or comissioning. Thewe validation steps completed by May 2018 | 4 | 10 | Med
2017-02-24 | 30 | Complications with winter ice | Extreme events | Technical | R. Tyler (lead engineer) | 8 | 10 | High | Collection of in river ice data for 2 years prior to deployment feeds engineeering and IO&M planning, June 2017- June 2018. ON device ice monitoring allows for operational state modification if adverse conditions or interactions occure | 6 | 10 | High
2017-02-24 | 31 | Adverse salmon smolt interactions | Normal power production | External | N. Johnson (environmental) | 8 | 8 | High | Develop rigorous fish monitroing pland in budget period 2. Consulst with state and federal agencies reularly to ensure study plan and instrumentation provides adeqaute infoarmaton for decision making, operate device only under continuoius montiroring during smolt outmigration | 6 | 8 | Med
2017-02-24 | 32 | Device removal complications | Commissioning | Technical | M. Worthington (Project Management) | 6 | 10 | High | Buoyancy system includes redundant and isoalted retrieval mechanisms, pre testing In Nikiski to reduce risk of retreival issues arrising | 4 | 10 | Med
2017-02-24 | 33 | Higher cost for maintenance and logistical support required | Normal power production | Commercial | M. Worthington (Project Management) | 8 | 8 | High | Developing system requirements will be critical for determining technical scope for operations and maintenance technical support; involve local resources and include 3rd party input to accurately ascertain feasibility of proposed systems for logistical and technical requirements in remote environment. Develop trained leads during project who will be responsible for operating the systems after the project. | 4 | 4 | Low

## Output Requirements
The following columns are mandatory for the final risk registers. Additional columns may be added, if information is provided in the input files (ex. date, additional comments etc):
Risk ID | If not provided, any identifier may be used.
Risk Description
Project Stage | Required for construction or project based risk registers.
Project Category
Risk Owner
Mitigating Action
Likelihood (1-10) | If multiple stages, all should be reflected in the output
Impact (1-10)
Risk Priority (low, med, high)