## Simplified Register
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
| 9 | The Council’s ability to cope with a natural disaster. ¦ Effects: Natural disaster; malicious or accidental incident affects support required by civilians or disrupts existing Council services. | Operations | Emergency Planning | CMT | 4 | 5 | Low | • Emergency plan • Emergency planning exercises beyond the district • Business continuity plans • Regular exercise and joint public sector workshops for Emergency Planning • Emergency Planning Communication s Strategy • Review of approach with partner organisations as a result of lessons learned from ‘near miss’ flood events. • Local Resilience Forum ¦ • Regularly test Emergency Plan • Test Service Business Continuity Plans • Ensure key emergency planning staff attend regular liaison meetings and training | 4 | 4 | Low
| 4 | Failure of IT systems ¦ Effects: Failure to secure and manage data leads to loss of/ corruption of / inaccuracy of data, results in disruption to services and breaches of security. A further consequence could be financial penalties and reputational risk. | Operations | Information Technology |  | 5 | 5 | Med
| 17 | Political changes in national priorities ¦ Effects: Changes in national political priorities may result in immediate changes that require additional resource to achieve and fail to reflect priorities determined by consultation. | Operations | Corporate Risk |  | 4 | 5 | Low
| 3 | Failure of contractors and suppliers working on the Council’s behalf ¦ Effects: Failure of contractor or partners to deliver services or meet agreed performance objectives leads to additional costs or failed objectives. | Operations | Financial | CMT | 4 | 4 | Low | • Procurement processes – including financial aspects/ contract standing orders/ equality standards • Contract process – creation of robust contracts • Accountability and risk ownership documented • Service Level Agreements • Contract monitoring • Trained/skilled staff • Project management • Relationship Management • Business Continuity Plans ¦ • Regular monitoring of contracts and performance by Managers. • Ensure that contracts have risk registers and mitigation in event of contract failure. | 4 | 3 | Low
| 10 | Major health and safety incident ¦ Effects: Major Health & Safety incident at Council leads to costs for inquiry, disruption to service and possible prosecution | Operations | Financial | 12 | 4 | 4 | Low
| 16 | Service provision affected by organisational change ¦ Effects: Service provision and performance affected by organisational change, industrial action and/or staff sickness resulting in complaints, poor performance and possible further costs. land District Council | Operations | Financial | Peter Catchpole ge 14 of 29 |  |  |  | • Working environment / org culture • Staff Committee • Consultation with Staff Side • Flexible working • Established suite of people policies & procedures • Business continuity plans • Management training • “Springboard” appraisal for all staff support and development • CMT monitor and lead on human resource management. • Regular performance monitoring and management • IIP • Access to interim arrangements • Robust sickness absence management • Project management processes k Register – Update ¦ • Business continuity plans for each service. • Culture of Council remains effective • Workforce planning, which includes succession planning for key roles an talent management • A comprehensive programme of health surveillance for groups of employees who work in certain service areas (e.g. refuse drivers, workshop, port staff, etc.) • Trained Mental Health First Aiders in place • Stress awareness training • Resilience training • Staff engagement and consultation processes | 4 | 3 | Low
| 1 | Legislative changes ¦ Effects: Changes arising from Central Government or EU legislation requiring significant alteration to organisational capacity, such as impact of welfare reform and universal credit, effects of devolution, introduction of new burdens. Risk of GDPR breach and ICO sanction/fine | Operations | Information Technology |  | 5 | 5 | Med | 10
| 2 | Brexit ¦ Effects: Uncertainty during transition period, followed by potential legislative, funding and policy changes after UK leaves EU may adversely affect the Council and its ability to provide services. | Operations | Information Technology | Peter Catchpole / Carol Pilson | 5 | 5 | Med | • Horizon scanning by Legal Services / CMT / Heads of Service • Financial & workforce planning • Membership of professional and Local Govt bodies aids horizon scanning • Management of change approach to mitigate against significant impact to the organisation and its staff • Detailed project plans to manage implementation of changes ¦ • Understanding and acting on intelligence from LGA, CIPFA and other local government sources. • Identifying policies that require changing, their effects and governance as Brexit effects start. | 3 | 2 | Low
| 8 | Funding changes make Council unsustainable ¦ Effects: Economic changes, imposed savings requirements, changes to local government funding systems, uncertainties of pilot pension fund. Financial Mgt of NNDR, CTS leads to change in income /spending making Council unsustainable. | Operations | Information Technology | 9 | 5 | 5 | Med | • • • • • •
| 11 | Fraud and error committed against the Council ¦ Effects: Potential for fraud, corruption, malpractice or error, by internal or external threats. In additional to immediate financial loss, this could harm reputation and lead to additional inquiry costs and penalties. | Operations | Financial | Peter Catchpole / Carol Pilson | 4 | 5 | Low | • Anti-fraud & corruption policy/ strategy • Financial Regulations / Standing Ord • Codes of conduct • Appropriately trained staff • Appropriate culture and risk awareness • Segregation of duties • Supported financial mgt system • Budget monitoring regime • Internal Audit review of sys /and controls • Bribery & corruption / fraud risk assessments • Indemnity insurance • Whistle-blowing procedure • Annual Governance Statement • ARP fraud resource • National Fraud Initiative ¦ • Increase staff vigilance • Fraud awareness training for Managers • Raise profile internally and externally for successful prosecutions | 3 | 3 | Low
| 13 | Failure of Governance in major partners or in the Council as a result of partnership working ¦ Effects: Partnership governance not adopted or followed, leading to unachieved priorities and poor performance by major partner agencies:- Cambs and Peterborough Combined Authority, Anglia Revenues Partnership, CNC Building Control, Shared Planning, Payroll delivered by Bedford BC. | Operations | Governance | 9 | 5 | 4 | Low
| 14 | Failure to achieve required savings targets ¦ Effects: Failure to achieve efficiency saving, maximise income, or performance targets, results in greater than budgeted costs and potential risk of Council not being able to set a balanced budget. | Operations | Financial | 9 | 5 | 4 | Low
| 18 | Capital funding strategy failure ¦ Effects: Financial risks of capital funding shortfalls leading to increased burden to the Council. Potential for marginal deficit in capital program if future funding is not realised | Operations | Information Technology | 9 | 4 | 5 | Low
| 19 | Poor communications with stakeholders ¦ Effects: Poor communication with stakeholders and staff leads to poorly informed direction of resources and lack of support for change Reputational damage Staff turnover Increased sickness absence | Operations | Human Resources | 9 | 5 | 4 | Low
| 7 | Lack of access to Council premises prevents services being delivered ¦ Effects: Disruption of service provision. | Operations | Governance | Peter Catchpole | 5 | 5 | Med | • Alarm and security systems • Fire drills • Business continuity plans • Emergency planning network • ICT disaster recovery and offsite testing • Relocation procedures - critical and support services • Geographically distributed sites • Remote working • Statutory building inspection and checks • Corporate Business Continuity Plans | 3 | 2 | Low

## Output Requirements
The following columns are mandatory for the final risk registers. Additional columns may be added, if information is provided in the input files (ex. date, additional comments etc):
Risk ID | If not provided, any identifier may be used.
Risk Description
Project Stage | Required for construction or project based risk registers.
Project Category
Risk Owner
Mitigating Action
Likelihood (1-10) | If multiple stages, all should be reflected in the output
Impact (1-10)
Risk Priority (low, med, high)